## Sheet1
Project name |  | Residential Flooring Renovation Project | Project Budget |  | $3000
Project Manager |  | Team 4 | Project Budget Sponcer |  | D.A George
[5 empty] | Budgeted Cost | Actual Cost | Under/ Over
ID | Task | Hours | Resourse | Resourse hr rate
1 | Purchasing the tiles | - | 1 Supply chain, 1 Procurement | - | $750 (25% of total budget) | 865.7 | 115.7
2 | Trasportation cost | 3 | 1 Supply chain, 1 Procurement | 100 | $300 (10% of total budget) | 300 | 0
3 | Inspecting the Current site | 2 | 1 PMO, 1 Site Engineer | 25 | $1950 (65% of total budget) | 50 | -1737.5
4 | Planning the project | 8 | 1 PMO | 25 |  | 200
5 | Removale of old tiles | 32 | Service provider | 15 |  | 480
6 | installation cost | 40 | Service provider | 15 |  | 600
7 | Final inspection | 6 | Service provider | 15 |  | 90
8 | New Tools and equpment cost |  | Service provider | 200 |  | 200
9 | Miscellaneous | 3 | - | 40 |  | 120
| Total | 94 |  |  | $ 3000 | $ 2905.70 | $ -94.30
1. Purchasing the tile ( Cost Estimation)
Room type |  | Area in Sq ft | Cost/ Sq fT | Total Cost per room in USD
Master Bedroom |  | 154 | 1.1 | 169.4
Bedroom 1 |  | 99 | 1.1 | 108.9
Bedroom 1 |  | 90 | 1.1 | 99
Dining room |  | 140 | 1.1 | 154
Kitchen |  | 100 | 1.1 | 110
Living Room |  | 204 | 1.1 | 224.4
| Total Area | $787 | Total cost | 865.7
1740
2905.7
[8 empty] | 787 | 865.7