## Sheet1
Risk Managment Report
Project Name | Residential Flooring Renovation Project | [5 empty] | Project Client | Project Client | D.A. George
fgtv
Risk ID | Risk Description |  |  |  | Likelihood of Occurrence (Low/Medium/High) |  |  | Impact on Project (Low/Medium/High) | Impact Description | Plan to Mitigate the Risk
R1 | Delays in delivery of new tiles |  |  |  | Medium |  |  | High | Could extend the project completion date, which can increased costs and disruption for operations | Maintain close communication with suppliers, have backup suppliers, and order materials well in advance.
R2 | Tiles not matching existing design |  |  |  | Low |  |  | Medium | Reordering the tiles causing slow down work and increased costs. | double check tile specifications before ordering and keep a sample on site.
R3 | Damage to existing flooring during removal |  |  |  | Medium |  |  | High | can lead to additional repairs extending the project timeline. | Use experienced contractors for removal and have a contingency budget for repairs.
R4 | Unavailability of skilled labor |  |  |  | High |  |  | High | Can delay the project and affect the quality of work. | Schedule work during off-peak periods, have a pool of backup labor, and provide training if necessary.
R5 | Unexpected structural issues |  |  |  | Low |  |  | High | Might necessitate structural repairs, significantly delaying the project and increasing costs. | Conduct a thorough site inspection before starting work and have a contingency budget.
R6 | Weather-related delays |  |  |  | Low |  |  | Medium | A bad weather can delay the project and affect the timeline. | Have a flexible schedule to accommodate delays.
R7 | Health and safety incidents |  |  |  | Medium |  |  | High | Can halt the project and lead to legal issues or compensation claims. | Implement strict health and safety protocols, provide training, and have emergency response plans.
R8 | Interruption to cafe operations |  |  |  | High |  |  | High | Could result in loss of revenue and customer dissatisfaction. | Plan work during non-peak hours, communicate with customers, and provide clear signage.
R9 | Budget overrun |  |  |  | Medium |  |  | High | Can affect the financial viability of the project and require additional funding. | Have a detailed budget with contingencies, monitor spending closely, and approve all changes formally.
R10 | Equipment failure |  |  |  | Low |  |  | Medium | May cause delays and additional costs for repairs or replacements | Regularly maintaince and keep backup equipment available, and train to use equipment
Risk Matrix
Severity
|  |  | Value times/ Days | Low |  | Medium |  | High
|  |  |  | 1 |  | 2 |  | 3
| Likelihood of Occurrence | High | 9 < |  |  |  |  | Unavailability of skilled labor
Interruption to cafe operations
|  | Medium | 5 to 8 | Equipment failure |  |  |  | Delays in delivery of new tiles
Damage to existing flooring during removal
Health and safety incidents
Budget overrun
|  | Low | 1 to 4 | Unexpected structural issues
Weather-related delays
Tiles not matching existing design
High Risk
Moderate risk
Low Risk